## Sheet1
TO-DO	Description	State	TEST
App Start Up	Building the structure of the application (The code base)	Done	Tested
Register a User	Implementing the logic for the user registeration	Done	Tested
Log In	Implementing the logic for user login	Done	Tested
Log Out	Implementing the logic for user log out	Done	Tested
Create a DB	Implementing the logic for database creation	Done	Tested
Connect to a DB	Implementing the logic for database connection	Done	Tested
Disconnect a DB	Implementing the logic for disconnecting from a database	Done	Tested
Close The App	Enabling the user to close the application safely	Done	Tested
Delete User	(Bonus): Delete a use from the system	Done	Tested
List Databases	List all the databases in the system	Done	Tested
Delete DB	Delete a database from the system	Done	Tested
Commands	List all The available commands	Done	Tested
NOW LETS ENTER THE DATABASE OPERATIONS
List Tables	List all the tables in the database	Done	Tested
Create Table	Create a new database Table	Done	Tested
Drop Table	Drop an existing table	Done	Tested
Truncate Table	Truncate a database Table	Done	Tested
Update	Update table rows	Pending	Not
Insert	Insert into a database table	Pending	Not
Select	Retrieving data from table	Working On	Not
Delete	Delete data from table	Working On	Not
Add Column	Add a new column to an existing table	Postponed	Not
Drop Column	Remove a column from an existing table	Done	Tested
Things To Consider
Primary Key	Make sure we don’t violate the PK Constraint	Pending	Not
Foreign Key	Make sure we don’t violate the FK Constraint	Pending	Not
Not Null	Make sure we don’t violate the Required Constraint	Pending	Not
Unique	Make sure we don’t violate the Unique Constraint	Pending	Not

NOTES
Green Rows means completed feature
Yellow Rows means a pending feature (Under construction)
Gray Rows with Red Status mean this feature is bonus (Will work on it after everything else is completed

Augmentations